## Slide 1: Øresund projects - Information on onshore transformer package
Marked dialog meetings during September 2020 to give initial introduction to the Øresund projects.
Project information may be changed at later stage

## Slide 2: HOFOR
Amagerværket: Biomass fired power station and district heating.
Offshore wind turbines
Waterworks
Town gas
Alternative district heating methods
District cooling
Renewable energy
Wastewater
Biogas

## Slide 3: The Øresund projects will be the visible proof that Copenhagen Municipality achieves CO2 neutrality in 2025
Capacity
~160 MW
...
NORDRE FLINT
AFLANDSHAGE
NORDRE FLINT (NFL):
~250 MW
AFLANDSHAGE (AHA):
FID
COD
2025
2023
2024
2022
2021
2020
Timeline
Start EU tender
Development
Construction
O&M
Location
Timeline
“The 1st carbon neutral capital city in the world”
Copenhagen Municipality can provide loan guarantees for the full project

## Slide 4: Aflandshage & Nordre Flint – project envelope
WTGs
Distance to shore
4 - 10 MW
Park capacity
Foundations
Up to 160 MW
...
NORDRE FLINT
Up to 250 MW
Gravity or monopile
(interface level: 3,7 - 4,0 m)
AFLANDSHAGE
O&M hub
TBD / CTV
Cables
(no OSS)
33 kV (~85 km)
66 kV (~55 km)
Grid connection point
At Amager Power Plant
Close to Avedøre Power Plant
Water depths
~2,6 - 17 m
~11 - 20 m
Tip height
Max 220
Lowest 20 m
~14 km
~17 km
...
NORDRE FLINT
AFLANDSHAGE
Cable corridor
Project area
Cable corridor
Project area
Mean wind
@ 120m
8,2 m/s
8,9 m/s
33 kV (~160 km) 66 kV (~90 km)

## Slide 5: HOFOR‘s objective is to run a lean and efficient project
The project shall be built with known and reliable technology
Known
technology
With a lean and efficient project delivery model, HOFOR relies on competent/ expert suppliers – whom will have freedom to focus on delivering their scope
Competency
& delivery
focused
To achieve a lean and efficient project execution, HOFOR focuses on limiting the number of interface in the project
Limited
interfaces

## Slide 6: In Denmark, Energinet.dk owns the grid from 132 kV - projects connect directly to the grid
HOFOR
HOFOR shall provide an area for the transformer station, construct the building, and deliver the switch gear.
HOFOR is responsible to transform from 33/66 kV to 132 kV and connect to existing grid in Energinet’s 132 kV station.
Maintenance of cables and switch gear up to the connection point is HOFOR’s responsibility (marked with red line)

## Slide 7: Export cable corridor for NFL to Energinet.dk’s 132kV station at Amagerværket (power plant owned by HOFOR)
Cable corridor in blue
Connection point red dot
Since Amagerværket is owned by HOFOR, the transformer station can be build on the premises
Energinet.dk is working towards establishing grid connection in 2023
2-4 cables to shore depending on number of WTGs & voltage levels
Potential cable crossings near land fall (export cable Middelgrunden Offshore Wind Farm) and in case Energinet.dk installs a 132 kV sea cable from Amager power plant to Svanemølle power plant
Cable corridor
Project area

## Slide 8: Nordre Flint – preliminary cable scenarios (no OSS)
16 x 10 MW WTGs
2 landfall cables
Spare cables not included
33 kV
66 kV
28 x ~5 MW WTGs
4 landfall cables
Spare cables not included
 |  | Cables length [km] | # cables
Small CSA mm2 | 300 | 13,5 | 10
Big CSA mm2 | 800 | 40,7 | 6
Total |  | 54,1 | 16
 |  | Cables length [km] | # cables
Small CSA mm2 | 300 | 12,2 | 18
Big CSA mm2 | 800 | 72,1 | 10
Total |  | 84,3 | 28
Preliminary assumption regarding burial depth is 1 to 1,5 m
Due to hard soil conditions, rock-dumping may be required for ~10% of the cables

## Slide 9: Export cable corridor for AHA to Energinet.dk’s 132kV station near Avedøreværket (power plant)
Cable corridor
Project area
Cable corridor in green
Connection point red dot
Transformer station cannot be build on the premises of Avedøreværket
Suitable onshore area identified in the vicinity of Avedøreværket - negotiations with land owners are progressing well
Energinet.dk is working towards establishing grid connection in 2023
3-6 cables to shore depending on number of WTGs & voltage levels
Two cables crossings (TDC and Global Connect) on the way to shore
Preliminary and indicative location of onshore substation

## Slide 10: Aflandshage – preliminary cable scenarios (no OSS)
25 x 10 MW WTGs
3 landfall cables
Spare cables not included
 |  | Cables length [km] | # cables
Small CSA mm2 | 300 | 41,2 | 15
Big CSA mm2 | 800 | 46,8 | 10
Total |  | 88,0 | 25
33 kV
66 kV
44 x ~5 MW WTGs
6 landfall cables
Spare cables not included
 |  | Cables length [km] | # cables
Small CSA mm2 | 300 | 31,3 | 24
Big CSA mm2 | 800 | 127,3 | 20
Total |  | 158,6 | 44
Preliminary assumption regarding burial depth is 1 to 1,5 m
Due to hard soil conditions, rock-dumping may be required for ~10% of the cables

## Slide 11: The transformer station is expected to be build on a 1000 m2 area with a size of 360 m2*